## Sheet1
Task number | Responsible | Expected artifact | 01.09.2021 | 01.10.2021 | 01.11.2021 | 01.12.2021 | 01.01.2022 | 01.02.2022 | 01.03.2022 | 01.04.2022 | 01.05.2022 | 01.06.2022 | 01.07.2022 | 01.08.2022 | 01.09.2022 | 01.10.2022
1.1 | Saar | Preparing report tasks: 1,2,7 | Preparing report
1.2 | Naor | Preparing report tasks: 3,4,5,6 | Saar | Preparing report tasks: 1,2,7
1.3 | Naor + Saar | Preparing report | Naor | Preparing report tasks: 3,4,5,6
2.1 | Naor + Saar | understanding all the theoretical aspects of the simulator |  | Naor + Saar | Preparing report
2.2 | Saar | Simulation of roads infrastructure on a map |  |  | Simulation running
2.3 | Naor | Simulation of various vehicles with metrics |  |  | Naor + Saar | understanding all the theoretical aspects of the simulator
3.1 | Naor | Progress report tasks: 4,5,7,8,9,10 |  |  |  | Saar |  | Simulation of roads infrastructure on a map
3.2 | Saar | Progress report tasks: 1,2,3,6,11,12 |  |  |  | Naor |  | mulation of various vehicles with metrics
3.3 | Naor + Saar | Final progress report |  |  |  |  | Prpgress report
4.1 | Naor + Saar | Simulation runs with GT |  |  |  |  | Naor | Progress report tasks: 4,5,7,8,9,10
4.2 | Naor + Saar | DTLS POC running |  |  |  |  | Saar | Progress report tasks: 1,2,3,6,11,12
4.3 | Naor + Saar | DTLS and GT Integration |  |  |  |  | Naor + Saar | Final progress report
5.1 | Naor | Presentation | [5 empty] | GT and DTLS integration
5.2 | Saar | Poster + POC | [5 empty] | Naor + Saar |  | Simulation runs with GT
5.3 | Naor + Saar | Syncing tasks 5.1 and 5.2 | [5 empty] | Naor + Saar |  |  |  |  | DTLS POC running
6.1 | Saar | Python project is containerized | [9 empty] | Naor + Saar |  | DTLS and GT Integration
6.2 | Naor | DB and Grafana running in containers | [10 empty] | Projects day + practical presentation
6.3 | Naor + Saar | Integration of all the containers | [10 empty] | Naor | Presentation
7.1 | Naor + Saar | Proof of DTLS correctness | [10 empty] | Saar | Poster + POC
7.2 | Naor + Saar | Project is finished | [10 empty] | Naor + Saar | Syncing tasks 5.1 and 5.2
7.3 | Naor + Saar | Project book is ready | [11 empty] | Present all the collected data in Grafana
[14 empty] | Saar | Python project is containerized
[14 empty] | Naor | DB and Grafana running in containers
[15 empty] | Naor + Saar | Integration of all the containers
Project book + working project
[15 empty] | Naor + Saar | Proof of DTLS correctness
[15 empty] | Naor + Saar | Project is finished
[15 empty] | Naor + Saar | Project book is ready